## Cover
Scrum Reporting Form
| Day | 2023-11-16
| Due Date | 2023-11-17
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
macro module
| Plans for | 2023-11-17
| Team Member | Tasks planned | Prriority
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants including Professor Cook | 3
| Story behind your project | The Dino Runner game is a small program made by google that has existed in their chromium browser for some time now. The program is a simple, small game of a dino running across the screen towards an unknown goal; However, while on his perilous journey, the dino comes across many cacti and flying obsticles. The goal is to recreate this game, aswell as put a unique spin on it

## 17 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-11-17 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-11-28
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-11-17 | Priority | Status
| Team Member | Tasks planned
| All | Decide on Project | 1 | Complete
| All | Identify major parts of the project | 2 | Pending
| Adam | Set up GitHub account and invite all participants including Professor Cook | 3 | Complete
| Plans for | 2023-11-28
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | 1
| Jessica | Create Sprites | 3
| Adam/Iszabella | Complete Programming | 3

## 28 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-11-28 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-11-30
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-11-28 | Priority | Status
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | 1 | ~75% Complete
| Jessica | Design placeholder sprites | 3 | Complete
| Adam/Iszabella | Begin programming | 3 | Complete
| Plans for | 2023-11-30
| Team Member | Tasks planned
| Jessica | Design initial sprites | 2 | Not started
| Adam | Begin developing core game concepts | 3 | Not started
| Bella | Design game balance | 2 | Not started

## 30 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-11-30 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-12-05
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-11-30 | Priority | Status
| Team Member | Tasks planned
| Jessica | Design initial sprites | 2 | Complete
| Adam | Begin developing core game concepts | 3 | ~80% Complete
| Bella | Design game balance | 2 | POSTPONED TO DEC 5 (Team memeber MIA)
| Plans for | 2023-12-05
| Team Member | Tasks planned
| Jessica | Refine Sprites/Design Backgrounds | 1 | Not Started
| Adam | Finish core game concepts/Begin work on sprite rendering | 2 | Not Started
| Bella | Design game balance | 4 | Not Started

## 5 Dec
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-12-05 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-12-07
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-12-05 | Priority | Status
| Team Member | Tasks planned
| Jessica | Refine Sprites/Design Backgrounds | 1 | Complete
| Adam | Finish core game concepts/Begin work on sprite rendering | 2 | Complete
| Bella | Design game balance | 4 | Complete
| Plans for | 2023-12-07
| Team Member | Tasks planned
| Jessica | Finish backgrounds | 2 | Complete
| Adam | Finish sprite rendering | 2 | Complete
| Bella | Finish scoring mechanisms | 2 | Complete

## 7 Dec
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-12-07 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-12-12
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-12-07 | Priority | 2023-12-06
| Team Member | Tasks planned
| Plans for | 2023-12-12
| Team Member | Tasks planned

## 12 Dec
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-12-12 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-12-14
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-12-12 | Priority | Status
| Team Member | Tasks planned
| Adam | Remove unecissary code and add doc strings | 3 | 50% Complete
| Jessica | Complete presentation | 4 | 75% Complete
| Izsabella | Complete presentation | 4 | 75% Complete
| Plans for | 2023-12-14
| Team Member | Tasks planned for Project Presentration
| Adam | Reflect | 1
| Jessica | Reflect | 1
| Izsabella | Reflect | 1

## 14 Dec
Scrum Reporting Form |  |  | Priority | Status
| Date | 2023-12-14 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2023-12-15
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-12-14 | Priority | Status
| Team Member | Tasks planned
| Plans for | 2023-12-15
| Team Member | Tasks planned for Project Presentration
| all | Final testing of software
Finish slide presentation and submit to D2L
Do video description of project and submit to D2L
Notify Professor Cook that GitHub is ready to download
Notify Professor Cook that D2L is ready to peruse also.

## Final
Scrum Reporting Form |  |  | Priority | Status | Final Thoughts on this Process
| Day | 2023-12-15 |  | Either DONE or what problem needs to be solved before the task can be completed. | This page is the last Scrum Form due and is to record your final thoughts on the process
| Due Day | 2023-12-15
| Team Name: | Segmentation Fault
| Team Members: | Adam Duncan, Izsabella Mendez, Jessica Ayala
| Project: | Dino Runner
Division of Labor
| Module Name | Author
| Pygame Display | Adam Duncan
| Collision detection | Adam Duncan
| Score Calculation | Iszabella Mendez
| Game Balance | Iszabella Mendez
| Sprite Creation | Jessica Ayala
| Tasks Due | 2023-12-15 | Priority | Status
| Team Member | Presentaion | Prriority
| all | Final testing of software | 1
| 0 | Finish slide presentation and submit to D2L
| 0 | Do video description of project and submit to D2L
| 0 | Notify Professor Cook that GitHub is ready to download
| 0 | Notify Professor Cook that D2L is ready to peruse also.
| Plans for | 2023-12-15
| Team Member | Tasks planned
Thgere are no tasks left to complete